## Source of Project Cost
Source of Project Cost
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK
PROJECT DESIGN | Develop Functional Specifications | 10 | 250 | 100 | 0 | 20 | 370
| Develop System Architecture | 30 | 750 | 600 | 0 | 200 | 1550
| Develop Preliminary Design Specification | 10 | 250 | 155 | 0 | 30 | 435
| Develop Detailed Design Specifications | 15 | 375 | 320 | 0 | 70 | 765
| Develop Acceptance Test Plan | 10 | 250 | 115 | 0 | 150 | 515
| Subtotal | 75 | 1875 | 1290 | 0 | 470 | 3635
PROJECT DEVELOPMENT | Develop Components | 40 | 1000 | 320 | 0 | 60 | 1380
| Procure Software | 10 | 250 | 850 | 300 | 200 | 1600
| Procure Hardware | 10 | 250 | 950 | 120 | 45 | 1365
| Development Acceptance Test Package | 10 | 250 | 220 | 0 | 75 | 545
| Perform Unit/Integration Test | 25 | 625 | 140 | 0 | 150 | 915
| Subtotal | 95 | 2375 | 2480 | 420 | 530 | 5805
PROJECT DELIVERY | Install System | 10 | 250 | 100 | 0 | 220 | 570
| Train Customers | 20 | 500 | 420 | 300 | 60 | 1280
| Perform Acceptance Test | 15 | 375 | 450 | 80 | 200 | 1105
| Perform Post Project Review | 5 | 125 | 30 | 90 | 45 | 290
| Provide Warranty Support | 5 | 125 | 120 | 120 | 75 | 440
| Archive Materials | 15 | 375 | 160 | 0 | 150 | 685
| Subtotal | 70 | 1750 | 1280 | 590 | 750 | 4370
PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 10 | 250 | 250 | 300 | 120 | 920
| Internal Status Meetings/Reports | 10 | 250 | 320 | 210 | 45 | 825
| Third-Party Vendor Interface | 15 | 375 | 520 | 320 | 75 | 1290
| Interface to Other Internal Departments | 10 | 250 | 105 | 120 | 150 | 625
| Configuration Management | 10 | 250 | 320 | 140 | 60 | 770
| Quality Assurance | 15 | 375 | 220 | 120 | 200 | 915
| Overall Project Management | 10 | 250 | 410 | 220 | 45 | 925
| Subtotal | 80 | 2000 | 2145 | 1430 | 695 | 6270
Subtotals |  | 320 | 8000 | 7195 | 2440 | 2445 | 20080
Risk (Contingency) |  | 10 | 250 | 200 | 0 | 25 | 475
Total (Scheduled) |  | 330 | 8250 | 7395 | 2440 | 2470 | 20555

## Expenditures Over Time
Expenditures Over Time
| ITEM | COST | DATE | REASON FOR EXPENDITURE
INSTALLATION | Install System | 0
| Train Customers | 0
| Perform Acceptance Test | 0
| Perform Post Project Review | 0
| Provide Warranty Support | 0
| Achieve Materials | 0
| Subtotal | 0
PLANNING (RFP) | Install System | 0
| Train Customers | 0
| Perform Acceptance Test | 0
| Perform Post Project Review | 0
| Provide Warranty Support | 0
| Achieve Materials | 0
| Subtotal | 0
PLANNING 2 | Install System | 0
| Train Customers | 0
| Perform Acceptance Test | 0
| Perform Post Project Review | 0
| Provide Warranty Support | 0
| Achieve Materials | 0
| Subtotal | 0
CONSTRUCTION | Install System | 0
| Train Customers | 0
| Perform Acceptance Test | 0
| Perform Post Project Review | 0
| Provide Warranty Support | 0
| Achieve Materials | 0
| Subtotal | 0
TEST & DELIVERY | Install System | 0
| Train Customers | 0
| Perform Acceptance Test | 0
| Perform Post Project Review | 0
| Provide Warranty Support | 0
| Achieve Materials | 0
| Subtotal | 0
PROJECT TOTAL |  | 0

## Data Worksheet
Project Data Worksheet
MONTH | PROJECTED MONTHLY COST | ACTUAL MONTHLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
1 | 1940 | 1610 | 2360 | 2750
2 | 1480 | 3190 | 1490 | 2950
3 | 1390 | 1930 | 1720 | 2510
4 | 4030 | 1370 | 1590 | 2330
5 | 3640 | 3680 | 4040 | 3650
6 | 2480 | 1180 | 3430 | 1840
7 | 3040 | 2390 | 1700 | 1660
8 | 2160 | 4040 | 3330 | 3300
9 | 1600 | 1330 | 1050 | 2980
10 | 2300 | 1140 | 2450 | 2990
11 | 3070 | 4210 | 3620 | 3540
12 | 2300 | 3910 | 1330 | 2230
13 | 1920 | 1580 | 4210 | 3910
14 | 3140 | 3850 | 1580 | 1500
15 | 2850 | 4000 | 3520 | 3020
16 | 2060 | 3700 | 1320 | 2590
17 | 1760 | 2900 | 3220 | 2990
18 | 3740 | 1870 | 3480 | 3660
19 | 3670 | 2180 | 3980 | 1230
20 | 3230 | 2790 | 3710 | 2190
21 | 2140 | 2550 | 1550 | 1940
22 | 1260 | 3890 | 2620 | 2470
23 | 3750 | 1850 | 2490 | 2170
24 | 2880 | 1740 | 2220 | 2140